## Slide 1
Jason McNeal, Ph.D. Partner
July 23, 2021
Campaign Readiness Study Update

## Slide 2: Overview
Since We Last Met – March 2020
Campaign Readiness Study Updated Timeline & Overview
What We Are Learning
Next Steps
Questions

## Slide 3: Since We Last Met March 2020
Timeline for Study Completion:
  From September 2020 until September 2021
Fall of 2020 – Identification of Campaign Priorities to Test
Spring 2021
  Creation of the “Stay Gold” Preliminary Case Statement for Testing
  Collection of Foundation Data and Materials
May 2021 - Interviews with Major Donors and Prospects

## Slide 4: Updated Study Timeline
July – August 2021
  Completion of Study Interviews – 36 completed
August – September 2021
  Final report prepared with recommendations
  Campaign with recommendations approved
October 2021
  Campaign begins

## Slide 5: Campaign Readiness Study Overview
University of North Alabama Foundation Campaign Readiness Study |  | 
Element | Title | Fundamental Question Answered
I | Internal Program Assessment | Preparedness: How internally prepared is the Foundation to successfully implement a campaign?
II | External Market Assessment | Feasibility: To what degree and in what ways are external constituents committed to UNA and supportive of the campaign priorities being proposed?
III | Report and Recommendations | What must the Foundation do to enhance the likelihood of a successful campaign?
IV | Proposed Campaign Plans | What are the steps necessary to implement an effective campaign plan?

## Slide 6: What Have We Learned So Far?
Preparedness - Institution
  Leadership Matters – President Ken Kitts
  Leadership Matters II – Administrative Team
  Enrollment Growth – 9 consecutive semesters
  Project 208 success
  Timing with broader economy

## Slide 7: What Have We Learned So Far?
Preparedness – Advancement Program
  A focus on policies and procedures
  Clear understanding of roles and responsibilities
  Communication across campus
  Improved data hygiene and expansion
  Stronger athletics/advancement interaction
  Innovating the President’s Cabinet ($1,000+ annual giving)
  Legacy Initiative success

## Slide 8: Feasibility: What Are We Testing?
Renovation of Music Building $15 million
Construction of New
Engineering Building $8 million
Student Scholarships $10 million
Leadership Scholarship Prog. $5 million
Athletics Stadium $25 million
Academic Innovation Fund $5 million
Mitchell-West Center for
Social Inclusion $1 million
Total $69 million

## Slide 9: What Have We Learned So Far?
Key Feasibility Assessments – To Date
  Strong, positive sentiment for UNA
  All priorities are viewed as “important to UNA’s future”
  UNA is positioned positively as a philanthropic priority, but work still to do
  Major gift capacity is positive, engagement remains the focus
  $69 million goal – 3.83 score on scale of 1-5
  Not known whether Boards can/will provide giving leadership

## Slide 10: Next Steps
Complete remaining confidential interviews with donors
Work with advancement team to finalize data/findings
Finalize study findings and develop recommendations
September 10 – Deliver study findings and recommendations
  Engage Campaign Steering Committee
  Refine Case Statement
  Commence Quiet Phase

## Slide 11: Questions? Thank You
Jason McNeal, Ph.D.
865.850.1164 – mobile
jmcneal@gonsergerber.com
www.gonsergerber.com